## Product_Backlog
Product Name:	Robbie Robot Shop					Fields in blue expect your input!
Team ID:	Binboi PD

Name:	Phuoc Do
Initials:	PD
Student ID:	1001239680

(Additional names for teams only)
Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Total Features	Left	Available	Completed	Sprint Ends
Total at Start	32	32
Sprint 1	32	32	1	Mar 28
Sprint 2	31	32	3	Apr 04
Sprint 3	29	32	7	Apr 11
Sprint 4	25	32	11	Apr 18
Sprint 5	21	32	11	Apr 25
Sprint 6	21	32	11	May 02

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Sprint # (by team size)					Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID	Prio	Status	Actual Sprint #	1	2	3	4	Pts	Cml	As a...	I want to...	So that...	Type	Notes
CRP	1	CP	1	1	1	1	1	21	21	PM	create robot parts	I can define robot models	CLI	No menu required here – run program, create a part
DRM	2	CP	2	2	1	1	1	13	34	PM	define new robot models	RRS can sell them to our Beloved Customers	CLI	Menu needed – create parts, then create a robot model
BRM	3	CP	2	2	1	1	1	5	39	BC	browse a catalog of robot models	I can buy one or more robots	CLI	Need to list robots models, then list parts in selected model
BC	4	CP	3	3	2	1	1	3	42	PB	create a new Beloved Customer	I can keep track of who's buying our products	CLI	The usual name, customer number, phone number, and email address
SA	5	CP	3	3	2	1	1	3	45	PB	create a new Sales Associate	I can keep track of my employees' performance	CLI	Name and employee number at a minimum
ORD	6	CP	3	3	2	2	1	8	53	SA	create a robot order for a Customer	I can sell robots and thus do my job well	CLI	Select robot model and quantity, show details with total price
DAT	7	CP	3	3	2	2	2	13	66	PB	ensure persistence of the RRS data	we don't lose orders or historical data	CLI	(CLI) Write the data to the default filename and reload it next time the program runs
OPEN_GUI	8	CP	4	4	3	2	2	3	69	All	open a GUI main window	I can interact with RRS Manager with my mouse	GUI	No menu required here – run program, create a part
GUI_CREATE_PART	9	CP	4	4	3	2	2	34	103	PM	create robot parts via GUI dialogs	I can define robot models	GUI	An fl_input centric approach is OK initially, but a custom dialog is worth bonus points (perhaps Create > Robot Part)
GUI_CREATE_MODEL	10	CP	4	5	4	3	3	21	124	PM	define new robot models via GUI dialogs	RRS can sell them to our Beloved Customers	GUI	Similar to robot parts (perhaps Create > Robot Model)
GUI_CATALOG	11	CP	4	6	4	3	3	8	132	BC	browse a catalog of robots via a GUI report	I can buy one or more robots	GUI	A text output is OK initially, but an attractive HTML-like output is desired (perhaps Report > All Robot Models)
	12	NS			5	4	3	21	153	SA	create a robot order for a Customer via GUI	I can sell robots and thus do my job well	GUI	As with CLI (and you’ll need the CLI to add BC and SA people)
	13	NS			5	4	4	13	166	PB	manage a robot order for a Customer via GUI	I can ensure the robot is built and ships	GUI	This will involve a state machine implementation
	14	NS			5	4	4	8	174	PB	create a new Beloved Customer via GUI	I can keep track of who's buying our products	GUI	The usual name, address, phone number, and email address (perhaps Create > Customer)
	15	NS			5	4	4	5	179	PB	create a new Sales Associate via GUI	I can keep track of my employees' performance	GUI	Name and employee number at a minimum (perhaps Create > Sales Associate)
	16	NS			6	5	4	13	192	BC	see pictures of the robots in the GUI catalog	I can see what I'm buying	GUI	Add picture when defining robot model, and show it in the robot model report
	17	NS			6	5	4	5	197	PB	allow the users to save data explicitly via GUI	we can save data without exiting the program	GUI	Write the data to the default filename on command (perhaps File > Save to the default filename)
	18	NS			6	5	4	8	205	PB	allow the users to load data explicitly via GUI	we can manage multiple stores in different files	GUI	Read the data from a user-selected file on command (perhaps File > Open)
	19	NS			6	5	4	8	213	PB	allow the users to save data to a specified name via GUI	we can manage multiple stores in different files	GUI	Write the data to a user-selected file on command and make that fie the default (perhaps File > Save As)
	20	NS				5	5	13	226	PB / SA	view a report of orders per SA in the GUI	I can estimate the value of employees / / I can justify a raise	GUI	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	21	NS				6	5	21	247	All	enable basic login by role and customize the GUI	we don't have options that don't apply to our roles	GUI	User ID might be “sa” for Sales associate with a default password, via a dialog on launch (i.e., in main()),and then make inapplicable menu items inactive – keep it simple
	22	NS				6	5	13	260	All	enable copy and paste from text fields	we can save typing	GUI	Just implement this where the toolkit supports it – not all text widgets do, but it's easy where it's supported
	23	NS				6	6	13	273	BC	view my bill (invoice) in the GUI	I can pay for my robots	GUI	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Invoice)
	24	NS					6	8	281	BC	view my orders in the GUI	see what I have coming to me	GUI	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Orders by Customer)
	25	NS					6	8	289	SA	view a sales report in the GUI	I can justify a raise	GUI	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	26	NS					6	8	297	PB	view a report of all orders in the GUI	I can manage the company	GUI	A basic text report is fine (perhaps Report > All Orders)
	27	NS					6	13	310	All	Add multi-level undo	Worry less about making mistakes	GUI	This would be for each Create event (e.g., a new Customer) only (perhaps Edit > Undo)
	28	NS					21	331	BC	see a pie chart of a model's component costs	I can decide if I want a different model	GUI	Consider using Fl_Chart, q.v., (perhaps Report > Robot Model Cost Breakdown)
	29	NS					13	344	SA	create a bulk (2+) order for Customer via GUI	avoid proliferation of orders and paperwork	GUI	Allow more than one robot model (with respective quantity) on a single order
	30	NS					8	352	PM	hide robot parts via GUI	obsolete parts aren't accidentally used	GUI	Mark robot parts as “obsolete” and don't allow adding them to new robot models
	31	NS					8	360	PM	hide robot models via GUI	obsolete robots aren't ordered	GUI	Mark robot models as “obsolete” and don't allow adding them to new orders
	32	NS					21	381	SA	save a draft order and return to it later via GUI	I can multi-task between indecisive customers	GUI	Save an order that hasn't been complete, and allow SA to resume work on it later
Product Backlog Burn Chart
Features Remaining at Start of Sprint
Sprints

## Sprint_01_Backlog
Sprint #	1
Start on	3/21/17 12:00 AM
End on	3/28/17 08:00 AM
Demo on	3/27/17 12:00 AM

Total Tasks	16
Day 1 Left	8
Day 2 Left	8
Day 3 Left	8
Day 4 Left	8
Day 5 Left	8
Day 6 Left	0
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
RPC	CRP		Code	PD	Robot_part class	CP
	CRP		Test	PD	Test Robot_part	CP
SNP	CRP		Code	PD	Shop class:: create new robot part	CP
	CRP		Test	PD	Test Shop::create new robot part	CP
SRP	CRP		Code	PD	Shop class:: remove robot part	CP
	CRP		Test	PD	Test Shop::remove robot part	CP
SGP	CRP		Code	PD	Shop class:: get robot part	CP
	CRP		Test	PD	Test Shop::get robot part	CP
VMN	CRP		Code	PD	View::Main menu, Part menu	CP
VDP	CRP		Code	PD	View::Display part, display all parts	CP
CIN	CRP		Code	PD	Controller::get input, get command, validate input	CP
	CRP		Test	PD	Test Controller::input	CP
CNP	CRP		Code	PD	Controller::create new part, list all parts	CP
	CRP		Test	PD	Test Controller::new part	CP
CRP	CRP		Code	PD	Controller::remove part	CP
	CRP		Test	PD	Test Controller::remove part	CP
Sprint Burn Chart
Days
Tasks

## Sprint_02_Backlog
Sprint #	2
Start on	3/28/17 12:00 AM
End on	4/4/17 08:00 AM
Demo on	4/3/17 12:00 AM

Total Tasks	12
Day 1 Left	8
Day 2 Left	8
Day 3 Left	8
Day 4 Left	8
Day 5 Left	4
Day 6 Left	4
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
RMA	DRM		Code	PD	Robot_model::constructor, add part	CP
	DRM		Test	PD	Test Robot model::constructor, add part	CP
SNM	DRM		Code	PD	Shop::create new robot model, push back into vector	CP
	DRM		Test	PD	Test Shop::create robot model	CP
SRM	DRM		Code	PD	Shop class:: remove robot model from vector	CP
	DRM		Test	PD	Test Shop::remove robot model from vector	CP
CAM	DRM		Code	PD	Add feature Create model and Remove model to Controller	CP
	DRM		Test	PD	Test Controller	CP
VDM	BRM		Code	PD	Catalog -> View class::display a model	CP
	BRM		Test	PD	Test View::display a model	CP
CBM	BRM		Code	PD	Controller::feature browse models	CP
	BRM		Test	PD	Test Controller	CP
Sprint Burn Chart
Days
Tasks

## Sprint_03_Backlog
Sprint #	3
Start on	4/4/17 12:00 AM
End on	4/11/17 08:00 AM
Demo on	4/10/17 12:00 AM

Total Tasks	16
Day 1 Left	12
Day 2 Left	8
Day 3 Left	6
Day 4 Left	6
Day 5 Left	4
Day 6 Left	2
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
WBC	BC		Code	PD	Write Customer class	CP
	BC		Test	PD	Test Customer class	CP
WSA	SA		Code	PD	Write Sales associate class	CP
	SA		Test	PD	Test Sales associate class	CP
WOR	ORD		Code	PD	Write Order class	CP
	ORD		Test	PD	Test Order	CP
CAM	DRM		Code	PD	Add feature Create model and Remove model to Controller	CP
	DRM		Test	PD	Test Controller	CP
DP	DAT		Code	PD	Save and load Robot Parts	CP
	DAT		Test	PD	Test	CP
DM	DAT		Code	PD	Save and load Robot Models	CP
	DAT		Test	PD	Test	CP
DCS	DAT		Code	PD	Save and load Customers and Sales associates	CP
	DAT		Test	PD	Test	CP
DOR	DAT		Code	PD	Save and load Orders	CP
	DAT		Test	PD	Test	CP
Sprint Burn Chart
Days
Tasks

## Sprint_04_Backlog
Sprint #	4
Start on	4/11/17 12:00 AM
End on	4/18/17 08:00 AM
Demo on	4/17/17 12:00 AM

Total Tasks	24
Day 1 Left	20
Day 2 Left	15
Day 3 Left	13
Day 4 Left	13
Day 5 Left	8
Day 6 Left	4
Day 7 Left	2

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	OPEN_GUI	Window	Code	PD	Create main window	CP
2	OPEN_GUI	Window	Code	PD	Add callback to exit window on clicking 'X'	CP
3	OPEN_GUI	Menu Bar	Code	PD	Create a menu bar	CP
4	OPEN_GUI	Menu Bar	Code	PD	Add item "Exit" and associate callback function	CP
5	OPEN_GUI	Menu Bar	Test	PD	Test window and menubar	CP
6	CREATE_ROBOT_PART	Controller	Code	PD	Turn private variables of Controller to global variables as well as member functions to free functions for GUI callbacks.	CP
7	CREATE_ROBOT_PART	Utility	Code	PD	Change utility functions (get_int, get_string,…) from CLI to GUI	CP	GUI callback functions cannot be member functions
8	CREATE_ROBOT_PART	Menu Bar	Code	PD	Add item Create>Robot Component	CP
9	CREATE_ROBOT_PART	Callback	Code	PD	Add callback function to create Robot Component	CP	Update to Custom Dialogs next Sprint
10	CREATE_ROBOT_PART	Menu Bar	Test	PD	Test item Create>Robot Component	CP
11	CREATE_ROBOT_MODEL	Menu Bar	Code	PD	Add item Create>Robot Model	CP
12	CREATE_ROBOT_MODEL	Callback	Code	PD	Add callback function to create Robot Model	CP	Update to Custom Dialogs next Sprint
13	CREATE_ROBOT_MODEL	Menu Bar	Test	PD	Test item Create>Robot Model	CP
14	GUI_CATALOG	Menu Bar	Code	PD	Add item View>Robot Parts	CP
15	GUI_CATALOG	Text Dialog	Code	PD	Create a text dialog to view parts	CP
16	GUI_CATALOG	Callback	Code	PD	Add callback function to view Robot Parts dialog	CP
17	GUI_CATALOG	Menu Bar	Test	PD	Test item View>Robot Parts	CP
18	GUI_CATALOG	Text Dialog	Code	PD	Add item View>Robot Models and associate callback function	CP
19	GUI_CATALOG	Menu Bar	Code	PD	Create a text dialog to view Models	CP
20	GUI_CATALOG	Callback	Code	PD	Add callback function to view Robot Models dialog	CP	Update to Custom Chooser Dialog next Sprint
21	GUI_CATALOG	Menu Bar	Test	PD	Test item View>Robot Models	CP
22	GUI_CATALOG	Wrap up	Demo	PD	Test for bugs	CP
23	GUI_CATALOG	Wrap up	UML	PD	Update UML State Diagram and Class Diagram	CP
24	GUI_CATALOG	Wrap up	Delivery	PD	Ready for submission	CP
Sprint Burn Chart
Days
Tasks

## Sprint_NN_Backlog
Sprint #					*** Example Only – Set up a tab for EACH SPRINT ***
Start on
End on
Demo on

Total Tasks	0
Day 1 Left	0
Day 2 Left	0
Day 3 Left	0
Day 4 Left	0
Day 5 Left	0
Day 6 Left	0
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
Sprint Burn Chart
Days
Tasks